## Project Schedule
PROJECT SCHEDULE TEMPLATE
Using state space models vs traditional models for intermittent data forecasting | Ashwin
PROJECT DELIVERABLE | Forecasting Pipeline
SCOPE STATEMENT | Evaluate and compare the forecasting accuracy of State Space Models (SSM) and Temporal Fusion Transformers (TFT) on intermittent time-series data
START DATE | END DATE | OVERALL PROGRESS
2026-02-09 | 2026-03-24 | 0%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | COMMENTS
GitHub Repo creation | Chirag | 2026-02-09 | 2026-02-10 | 2 | Complete
EDA | Rohan | 2025-02-11 | 2025-02-20 | 5 | Complete
Evaluation metrics | Ashwin | 2025-02-11 | 2025-02-20 | 6 | Complete
Data split & preprocessing | Chirag | 2025-02-11 | 2025-02-20 | 3 | Complete
TFT model development | Chirag | 2025-02-21 |  | 5 | In Progress
MLP + SSM model dev | Ashwin | 2025-02-21 |  | 2 | In Progress
SSM model dev | Rohan | 2025-02-21 |  | 5 | In Progress